RMMM (Risk Mitigation, Monitoring, and Management) Plan (Students are advised to have atleast 3-5 Risks from the project to showcase in the Risk Table)

Step 1: Forming a Risk Table: A risk table provides a simple technique for risk projection to the project manager. It consists of six columns:

- Risk ID: Unique identifier assigned to each risk

- Risk: Short description of the risk

- Risk Category*: Classification of risk (one of the seven categories: PS, BU, CU, PD, DE, TE, ST)

- Probability**: Estimation of the likelihood of risk occurrence based on group input

- Impact***: Severity of the risk if it occurs: Catastrophic / Critical / Marginal / Negligible

- RMMM (Risk Mitigation, Monitoring, and Management): Reference/pointer to the plan describing how the risk will be handled

Step 2: Sort the risks in descending order based on probability of risk occurrence.

Step 3: To form a Risk Information Sheet (RIS) for each individual risks separately.

Note: * - See below for better understanding.

*Risk Category Table

| Risk Category | Short Form | Explanation |
| --- | --- | --- |
| Product Size | PS | Risks related to the overall size, scale, and complexity of the software to be developed |
| Business Impact | BU | Risks arising from business constraints such as market conditions, competition, and management decisions |
| Customer Characteristics | CU | Risks related to customer behavior, expectations, and the ability to communicate effectively with them |
| Process Definition | PD | Risks due to unclear, undefined, or poorly followed software development processes |
| Development Environment | DE | Risks associated with the availability, reliability, and quality of development tools and infrastructure |
| Technology to be Built | TE | Risks due to the complexity, novelty, or uncertainty of the technology used in the system |
| Staff Size & Experience | ST | Risks related to the skills, experience, and availability of the development team |

**Assigning Probability (%) in Risk Analysis

- Define each risk clearly and specifically (avoid vague statements)

- Discuss with your project team members for estimation

- Each member independently assigns a probability (%) based on experience and knowledge

- Discuss all estimates within the group

- Finalize the probability using:  Average method or Consensus (agreed value)

- Use a standard probability scale:

| Range | Interpretation |
| --- | --- |
| 80% – 100% | Very High |
| 60% – 79% | High |
| 40% – 59% | Medium |
| 20% – 39% | Low |
| < 20% | Very Low |

***Risk Severity Category Table – Gives the value for Impact

| Category | Level | Performance | Support | Cost | Impact |
| --- | --- | --- | --- | --- | --- |
| Catastrophic | 1 | Failure to meet the requirement would result in mission failure | — | Failure results in increased costs and schedule delays with expected values in excess of $500K | 1 |
|  | 2 | Significant degradation to nonachievement of technical performance | Nonresponsive or unsupportable software | Significant financial shortages, budget overrun likely |  |
| Critical | 1 | Failure to meet the requirement would degrade system performance to a point where mission success is questionable | — | Failure results in operational delays and/or increased costs with expected value of $100K to $500K | 2 |
|  | 2 | Some reduction in technical performance | Minor delays in software modifications | Some shortage of financial resources, possible overruns |  |
| Marginal | 1 | Failure to meet the requirement would result in degradation of secondary mission | — | Costs, impacts, and/or recoverable schedule slips with expected value of $1K to $100K | 3 |
|  | 2 | Minimal to small reduction in technical performance | Responsive software support | Sufficient financial resources |  |
| Negligible | 1 | Failure to meet the requirement would create inconvenience or non-operational impact | — | Error results in minor cost and/or schedule impact with expected value of less than $1K | 4 |
|  | 2 | No reduction in technical performance | Easily supportable software | Possible budget underrun |  |

Step 1: Forming a Risk Table

| Risk ID | Risk | Category | Probability | Impact | RMMM |
| --- | --- | --- | --- | --- | --- |
| 1 | Backend integration failure | TE | 70% | 1 | Use modular architecture, test APIs regularly, debug endpoints |
| 2 | Data not persisting after restart | DE | 65% | 2 | Use SQLite database, avoid temporary storage, validate DB operations |
| 3 | Incorrect status calculation | PD | 60% | 2 | Implement backend logic and test with multiple vitals |
| 4 | File upload errors | TE | 50% | 3 | Validate file types, handle exceptions, store files properly |
| 5 | Alert system not triggering | PD | 55% | 2 | Implement trigger logic and test abnormal vitals scenarios |
| 6 | UI bugs (charts, tabs) | DE | 45% | 3 | Perform UI testing and fix responsiveness issues |
| 7 | Time constraints for Sprint completion | BU | 40% | 3 | Prioritize core features and follow sprint planning |
| 8 | Lack of team coordination | ST | 30% | 3 | Conduct regular meetings and task tracking |

Step 2: Sort the risks in descending order based on probability of risk occurrence.

| Risk ID | Risk | Category | Probability | Impact | RMMM |
| --- | --- | --- | --- | --- | --- |
| 1 | Backend integration failure | TE | 70% | 1 | Use modular architecture, test APIs regularly |
| 2 | Data persistence failure | DE | 65% | 2 | Implement SQLite properly |
| 3 | Incorrect status calculation | PD | 60% | 2 | Test logic thoroughly |
| 5 | Alert system not triggering | PD | 55% | 2 | Add trigger logic |
| 4 | File upload errors | TE | 50% | 3 | Validate files |
| 6 | UI bugs | DE | 45% | 3 | Perform UI testing |
| 7 | Time constraints | BU | 40% | 3 | Plan sprint tasks |
| 8 | Team coordination issues | ST | 30% | 3 | Regular meetings |

Step 3: To form a Risk Information Sheet (RIS) for each Risks separately.

Risk Information Sheet (RIS) for 70% Risk

| Risk ID: 1 | Date: 10/04/2026 | Probability: 70% | Impact: 1 |
| --- | --- | --- | --- |
| Description | Backend integration may fail due to incorrect API implementation or database connection issues. |  |  |
| Refinement & Context | Sub condition 1: APIs may not return correct data Sub condition 2: Database queries may fail Sub condition 3: Integration between frontend and backend may break |  |  |
| Mitigation & Monitoring Strategies | - Use structured API endpoints - Test each API using tools like Postman - Validate database queries - Monitor logs regularly |  |  |
| Contingency Plan and Management | - Debug and fix API issues immediately - Recheck database schema - Reintegrate frontend with backend |  |  |
| Trigger | API failures or incorrect data responses |  |  |
| Status | Monitoring in progress |  |  |
| Assigned To: Scrum Master Name |  | Originator: Risk Management Team |  |

| Risk ID: 2 | Date: 10/04/2026 | Probability: 65% | Impact: 1 |
| --- | --- | --- | --- |
| Description | Data may not be saved in the database, leading to loss of patient records after server restart. |  |  |
| Refinement & Context | Sub condition 1: SQLite not configured properly Sub condition 2: Data stored in temporary variables Sub condition 3: Database commit not executed |  |  |
| Mitigation & Monitoring Strategies |  Use SQLite database for all data storage  Ensure proper commit operations  Test data persistence after restart  Monitor database logs |  |  |
| Contingency Plan and Management | - Reconfigure database connection - Debug SQL queries - Restore backup data |  |  |
| Trigger | Data missing after refresh or restart |  |  |
| Status | Monitoring |  |  |
| Assigned To: Mohd. Farzeen Ajmal |  | Originator: Risk Management Team |  |

| Risk ID: 3 | Date: 10/04/2026 | Probability: 60% | Impact: 1 |
| --- | --- | --- | --- |
| Description | Patient status may be incorrect due to improper logic (e.g., abnormal vitals showing stable). |  |  |
| Refinement & Context | Sub condition 1: Status stored statically instead of computed Sub condition 2: Wrong threshold values Sub condition 3: Logic not updated after vitals change |  |  |
| Mitigation & Monitoring Strategies |  Implement backend status calculation  Test with different vitals datasets  Validate threshold conditions  Perform unit testing |  |  |
| Contingency Plan and Management | - Fix calculation logic - Update threshold rules - Re-test system |  |  |
| Trigger | Mismatch between vitals and status |  |  |
| Status | Resolved / Monitoring |  |  |
| Assigned To: Mohd. Farzeen Ajmal |  | Originator: Risk Management Team |  |

| Risk ID: 5 | Date: 10/04/2026 | Probability: 55% | Impact: 2 |
| --- | --- | --- | --- |
| Description | System fails to generate alerts for abnormal patient conditions. |  |  |
| Refinement & Context | Sub condition 1: Missing trigger logic Sub condition 2: Alerts not updated to vital update Sub condition 3: Logic not updated after vitals change |  |  |
| Mitigation & Monitoring Strategies |  Implement automatic alert generation  Link alerts with status calculation  Test abnormal cases  Monitor alert creation logs |  |  |
| Contingency Plan and Management | - Manually generate alerts - Fix backend trigger logic - Debug alert API |  |  |
| Trigger | No alert generated for critical vitals |  |  |
| Status | Monitoring |  |  |
| Assigned To: Mohd. Farzeen Ajmal |  | Originator: Risk Management Team |  |

| Risk ID: 4 | Date: 10/04/2026 | Probability: 50% | Impact: 2 |
| --- | --- | --- | --- |
| Description | System fails to generate alerts for abnormal patient conditions. |  |  |
| Refinement & Context | Sub condition 1: Backend not handling files correctly Sub condition 2: Invalid file formats Sub condition 3: Storage path issues |  |  |
| Mitigation & Monitoring Strategies |  Validate file types (PDF, JPG, PNG)  Configure upload folder properly  Handle exceptions  Test file uploads |  |  |
| Contingency Plan and Management | - Retry upload process - Fix file handling logic - Provide error messages |  |  |
| Trigger | Upload failure or missing file |  |  |
| Status | Monitoring |  |  |
| Assigned To: Mohd. Farzeen Ajmal |  | Originator: Risk Management Team |  |

| Risk ID: 6 | Date: 10/04/2026 | Probability: 45% | Impact: 3 |
| --- | --- | --- | --- |
| Description | UI issues like chart overflow, tabs not working, or layout problems. |  |  |
| Refinement & Context | Sub condition 1: Improper CSS styling Sub condition 2: JavaScript event issues Sub condition 3: Responsive design problems |  |  |
| Mitigation & Monitoring Strategies |  Perform UI testing  Fix CSS and layout issues  Test responsiveness  Debug JS events |  |  |
| Contingency Plan and Management | - Fix UI components - Re-test interface - Simplify design if needed |  |  |
| Trigger | UI not functioning as expected |  |  |
| Status | Resolved / Monitoring |  |  |
| Assigned To: Mohd. Farzeen Ajmal |  | Originator: Risk Management Team |  |

| Risk ID: 7 | Date: 10/04/2026 | Probability: 40% | Impact: 3 |
| --- | --- | --- | --- |
| Description | Project may not be completed within the sprint deadline. |  |  |
| Refinement & Context | Sub condition 1: Poor planning Sub condition 2: Underestimation of tasks Sub condition 3: Delays in development |  |  |
| Mitigation & Monitoring Strategies |  Prioritize core features  Follow sprint planning  Track progress regularly |  |  |
| Contingency Plan and Management | - Extend deadlines if possible - Reduce non-essential features - Allocate more time/resources |  |  |
| Trigger | Missed milestones |  |  |
| Status | Monitoring |  |  |
| Assigned To: Mohd. Farzeen Ajmal |  | Originator: Risk Management Team |  |

| Risk ID: 8 | Date: 10/04/2026 | Probability: 30% | Impact: 3 |
| --- | --- | --- | --- |
| Description | Project may not be completed within the sprint deadline. |  |  |
| Refinement & Context | Sub condition 1: Miscommunication Sub condition 2: Uneven task distribution Sub condition 3: Lack of collaboration |  |  |
| Mitigation & Monitoring Strategies |  Conduct regular meetings  Use task management tools  Assign clear responsibilities |  |  |
| Contingency Plan and Management | - Reassign tasks - Improve communication - Increase collaboration |  |  |
| Trigger | Delays due to coordination issues |  |  |
| Status | Monitoring |  |  |
| Assigned To: Mohd. Farzeen Ajmal |  | Originator: Risk Management Team |  |