## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
Backend integration was successfully implemented and connected to frontend. | Initial backend structure was not properly layered. | Follow layered architecture (API → Service → DB). | Refactor backend to maintain clean structure.
Data persistence was achieved using SQLite database. | Data loss issue existed initially after restart. | Use database for all modules instead of temporary storage. | Ensure all features use persistent DB storage.
Add Patient feature was fully functional with validations. | Input validation was missing in early stages. | Implement strict validation rules for all forms. | Add validation checks for all user inputs.
Dynamic patient status calculation was implemented. | Status was previously static and incorrect. | Always compute status from vitals instead of storing. | Move status logic to backend services.
Auto alert generation based on vitals was implemented. | Alerts were initially manual and not persistent. | Automate alert generation based on thresholds. | Implement alert triggers in backend logic.
Delete patient feature (CRUD operation) was added. | Related data (alerts, vitals) not deleted initially. | Use cascade delete for related records. | Ensure referential integrity in DB.
Dashboard now shows real-time data. | Dashboard was previously static. | Fetch data dynamically using APIs. | Connect dashboard to backend endpoints.
File upload and report handling was implemented. | Upload feature initially not working. | Implement backend file handling logic. | Validate file types and store properly.
Alerts system (Resolve/Unresolve) is fully functional. | Alerts state was not saved earlier. | Store alert status in database. | Ensure updates persist after refresh.
System became fully functional and demo-ready. | Some UI bugs (charts, tabs) existed earlier. | Improve UI testing and responsiveness. | Add testing phase before final demo.