## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
All core UI screens were completed successfully.Team collaboration was smooth.Frontend design matched requirements. | Backend integration was delayed.Data persistence issues occurred.Some features initially non-functional. | Introduce backend earlier in development.Use modular coding practices.Improve testing before demo. | Integrate backend from sprint start.Allocate time for testing.Fix bugs before submission deadlines.
Alerts system UI was implemented well.Dashboard visualization was clear. | Charts had overflow bugs.Tabs were not working initially. | Use tested chart libraries.Implement reusable components. | Add UI testing phase.Validate responsiveness early.
File upload UI was user-friendly. | Upload functionality was not working initially. | Implement backend APIs earlier.Test file handling thoroughly. | Add backend validation.Test file upload edge cases.
Team met sprint deadlines overall. | Requirement clarity issues at start. | Conduct better sprint planning.Clarify requirements early. | Define requirements clearly before sprint.