## Sheet1
Product Backlog
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Patient Data Collection | Patient Monitoring | As a healthcare system, I want to collect liver cirrhosis patient vitals and clinical data so that patient health can be monitored continuously. | Must | In Progress | 1. Patient vitals are captured periodically. 2. Clinical parameters are stored. 3. Data is linked to patient ID. 4. Missing data is handled. | Capture vital signs. Store clinical parameters. Link data to patient profile. | Response time < 2 seconds. Secure medical data storage. High availability. | 4 days | 4 days
2 | Symptom Tracking | Patient Monitoring | As a healthcare system, I want to track liver cirrhosis symptoms so that disease progression can be analyzed. | Must | In Progress | 1. Symptoms are logged by patient or clinician. 2. Severity levels are recorded. 3. Symptom history is maintained. | Symptom logging module. Severity classification. History tracking. | Fast data entry. Data consistency ensured. | 3 days | 3 days
3 | Alert Generation | Clinical Alerts | As a healthcare system, I want to generate alerts when patient parameters exceed thresholds so that timely medical intervention is possible. | Must | Pending | 1. Thresholds are predefined. 2. Alerts are triggered automatically. 3. Notifications are sent to clinicians. | Threshold evaluation engine. Alert generation. Notification service. | Alert latency < 5 seconds. High reliability. | 4 days | 4 days
4 | Risk Level Assessment | Clinical Decision Support | As a healthcare system, I want to assess patient risk levels so that high-risk liver cirrhosis patients are identified early. | Must | Backlog | 1. Patient data is analyzed. 2. Risk score is generated. 3. Risk category is assigned. | Risk scoring algorithm. Risk classification logic. Risk display. | Consistent scoring. Scalable processing. | 4 days
5 | Doctor Dashboard | Visualization | As a healthcare system, I want to provide a dashboard for doctors so that patient status can be viewed clearly. | Should | Backlog | 1. Patient summaries are displayed. 2. Alerts are highlighted. 3. Historical trends are shown. | Dashboard UI. Trend visualization. Alert indicators. | Page load time < 3 seconds. Usable interface. | 3 days
6 | Patient History Management | Medical Records | As a healthcare system, I want to maintain patient history so that long-term disease tracking is possible. | Should | Backlog | 1. Past records are stored. 2. Records are retrievable. 3. Data integrity is maintained. | Medical record storage. Search and retrieval. | Secure storage. Fast retrieval. | 3 days
7 | Report Generation | Reporting | As a healthcare system, I want to generate patient reports so that clinical decisions are supported. | Could | Backlog | 1. Reports are generated on demand. 2. Reports include vitals and risk level. 3. Reports are downloadable. | Report generation module. Export functionality. | Report generation < 5 seconds. Reliable output. | 3 days